## Sheet1
Last updated 12/15/14 Kelly Bundy (Surescripts)
Critical Path - Carequality Demo
ID | Task Name | Dependencies | Status | Deadline | Owner | Notes
1 | Demo prep
1a | Finalize location of demonstration | None | In process | 2015-01-05 |  | We need to decide physical location for the demo ASAP in order to create effective workflow scenarios. I recommend every vendor who is participating in this demo needs to be in the same physical location (whether that is the Interop Showcase or the Carequality/Healtheway/CCC booth) in order to show a coherent workflow demonstration. Each vendor is welcome to speak about the capability and the demonstration at their corporate booth, however it would not be in our best interest to provide live demos out of each respective booth. This does not give the audience a holistic view of the interoperability and workflow, it will provide an extra layer of technical difficulty and it would interfere with the live group demo given at the Carequality/Healtheway/CCC booth. The demos provided last year at the Interop Showcase were very successful as we were all in the same physical location and the demonstration flowed seamlessly between participants. Is the Carequality/Healtheway/CCC booth large enough to hold that many vendor participants? If it will be too congested, we should consider Interop Showcase participation.
1b | Finalize vendor participants | None | In process | 2015-01-31 |  | Outreach to all Carequality members to solicit participation. Get a technical and a marketing contact from each participant.
1c | Create patients/demographics | None | Not started | 2015-01-31 |  | We can refresh last year's Interop Showcase patients to minimize new work. Consolidated list of all patients, demographics and identifiers
1d | Final draft of demo scenarios | 1a, 1b, 1c | Not started | 2015-02-27 |  | Rough draft can be created before list of vendors is finalized, but ideally the vendor list will be solidified before the scenarios are written. We can refresh last year's Interop Showcase scripts to minimize new work
1e | Create technical scripts for scenarios | 1d | Not started | 2015-03-06 |  | We can refresh last year's Interop Showcase scripts to minimize new work
1f | Create speaking points | 1d | Not started | 2015-03-06 |  | We can refresh last year's Interop Showcase scripts to minimize new work
1g | Remote run-throughs | 1a, 1b, 1c, 1d, 1e | Not started | 2015-03-13 |  | Remote run throughs must be conducted early to give each vendor enough time to make needed adjustments prior to shipping hardware to HIMSS
1h | Onsite run-throughs | 1a, 1b, 1c, 1d, 1e | Not started | 2015-04-11 |  | Setup and practice on HIMSS show floor
2 | Create marketing materials
2a | Create sub group of marketing reps | 1b | Not started | 2015-01-31 |  | One marketing member from each participating vendor. All vendors need to be conveying the same message at their corporate booths and at the Carequality/Healtheway/CCC booth
2b | Create marketing plan | 2a | Not started | 2015-02-13
2c | Demo card handouts | 2b | Not started | 2015-03-20
2d | Carequality slide deck for each vendor's corporate booth | 2b | Not started | 2015-03-20
2e | Ads/PR content | 2b | Not started | 2015-03-20
2f | Q&A / FAQs for attendees | 2b | Not started | 2015-03-20
2g | Other marketing materials? | 2b | Not started | 2015-03-20
3 | Get demo system ready
3a | Determine standards being used | 1b | In process | 2015-01-31 |  | XCPD, XCA, HPD, etc
3b | Determine connectivity requirements | 1a, 1b, 3a | In process | 2015-01-31
3c | Populate each vendor system with patient information | 1c | Not started | 2015-02-13
3d | Populate each vendor system with participant information | 1b | Not started | 2015-02-13 |  | endpoints, etc
3e | Virtual connectivity testing | 3b | Not started | 2015-02-27
3f | Onsite connectivity testing | 3b | Not started | 2015-04-11 |  | at HIMSS
4 | Interop Showcase logistics
4a | Electrical survey | TBD | Not started | TBD |  | Not needed if not doing Interop showcase
4b | A/V equipment survey | TBD | Not started | TBD |  | Not needed if not doing Interop showcase
4c | Booth furniture | TBD | Not started | TBD |  | Figure out furniture setup/placement of participants
4d | Badge registrations | TBD | Not started | TBD |  | Not needed if not doing Interop showcase
5 | Attendee Logistics
5a | Create attendee contact list | 1b | Not started | 2015-04-08 |  | List with arrival times and phone numbers